## Master Schedule
SCOPE OF WORK |  |  | AUGUST |  |  |  | SEPTEMPER |  |  |  |  | OCTORBER |  |  |  |  | NOVEMBER |  |  |  |  | DECEMBER
|  |  | 3~7 | 10~14 | 17~21 | 24~28 | 31/10~4 | 7~11 | 14~18 | 21~25 | 28~30 | 1~4 | 7~11 | 14~18 | 21~25 | 28~30 | 1~4 | 7~11 | 14~18 | 21~25 | 28~30 | 1~4 | 7~11 | 14~18 | 21~25 | 28~30
UI DESIGN
DEVELOPMENT | Mobile App | HTML mockup
Implement with API
| Back End | Database Design
API Specs
Web Dev (Admin Panel)
API Develoment
INTERGRATION TEST
DEPLOYMENT
GO LIVE
12/01/2022

## HTMLMOCKTEACHER-Activity
HTML MOCKUP ACTIVITY
Author |  | Thach Nguyen
Create Date |  | 2020-09-13
Update Date | Quang | 2020-09-28
No | Module/Group | Task Name | Platform | Estimation (Hr) | PIC | Start date | End date | Actual (hr) | A PIC | A Start date | A End date | Status | Note
| Teacher | Master HTML | PC/Tablet |  | Tâm |  |  |  | Tâm |  |  | Done
Slide 6 | Teacher | Dashboard with no student | PC/Tablet |  | Tâm
Slide 47 | Teacher | Dashboard with existing students | PC/Tablet |  | Tâm
Slide 15 | Teacher | New Assignment Creation | PC/Tablet |  | Tâm
Slide 16 | Teacher | New Assignment Creation -> Filling data | PC/Tablet |  | Tâm
Slide 17 | Teacher | New Assignment Creation -> Filling data | PC/Tablet |  | Tâm
Slide 18 | Teacher | Assignment Confirmation | PC/Tablet |  | Tâm
Slide 19 | Teacher | Dashboarh with Group Progress info | PC/Tablet |  | Tâm
Slide 20 | Teacher | Create New menu button | PC/Tablet |  | Tâm
Slide 21 | Teacher | Search Experience | PC/Tablet |  | Tâm
Slide 24 | Teacher | Assignment Tab | PC/Tablet |  | Tâm
Slide 25 | Teacher | Assignment Creation within Assignment tab (when clicking "create new" button) | PC/Tablet |  | Tâm
Slide 26 | Teacher | Sound | PC/Tablet |  | Tâm
Slide 28 | Teacher | Messenging app | PC/Tablet |  | Tâm
Slide 29 | Teacher | Notification | PC/Tablet |  | Tâm
Slide 30 | Teacher | Lessons Tab (upcoming / past lessons) | PC/Tablet |  | Tâm
Slide 31 | Teacher | Lesson Confirmation | PC/Tablet |  | Tâm
Slide 34 | Teacher | Lesson Creation | PC/Tablet |  | Tâm
Slide 35 | Teacher | Assignment Creation (Followed after Lesson creation) Quite different from slide 15 -> nhưng cố gắng hợp nhất 2 slide thành mẫu đơn giản nhất có thể | PC/Tablet |  | Tâm
Slide 36 | Teacher | Màn hình đánh giá bài làm của học sinh | PC/Tablet |  | Tâm
Slide 41 | Teacher | Màn hình ghi nhận xét trên từng đoạn biểu diễn của học sinh, (phần next recording là các bài tập của những học sinh khác đã submit lên để giáo viên dễ dàng review ngay trong 1 màn hình | PC/Tablet |  | Tâm
Slide 42 | Teacher | Tính năng tặng sticker | PC/Tablet |  | Tâm
Slide 43 | Teacher | Từ Slide 41 phóng full màn hình và giấu đi các note mà học sinh gởi lên cho giáo viên | PC/Tablet |  | Tâm
Slide 44 | Teacher | Show sheet nhạc song song với video học sinh đang chơi để giáo viên tiện ghi chú và đánh dấu lên sheet nhạc | PC/Tablet |  | Tâm
Slide 50 | Teacher | Student Profile (activity board) | PC/Tablet |  | Tâm
Slide 51 | Teacher | Giáo viên vào xem nhận xét bài tập của một học viên cụ thể nào đó (slide 44 có thể link với slide này -> cần suy nghĩ thêm ;)) | PC/Tablet |  | Tâm
0

## StudentBasicDesign_Actovity
BASIC DESIGN ACTIVITY
Author |  | Thach Nguyen
Create Date |  | 2020-09-13
Update Date | Quang | 2020-09-28
No | Module/Group | Task Name | Platform | Estimation (Hr) | PIC | Start date | End date | Actual (hr) | A PIC | A Start date | A End date | Status | Note
0

## Coding-Activity
CODING ACTIVITY
Author |  | Thach Nguyen
Create Date |  | 2020-09-13
Update Date |  | 2020-09-23
No | Module/Group | Task Name | Estimation (Hr) | PIC | Start date | End date | Actual | A PIC | A Start date | A End date | Status | Note